## Possible Risks
Organization: NuovoDoc
Initiative, Project, and/or Engagement: ODMA Support Refresh
Date: 2004-11-18
Risk ID# | Possible Risks | Risk / Issue | Action / Disposition of Concerns, Issues, and Problems
1 | Loss of Connectivity to Site Prevents Updating | R | Technology - Operational Environment
2 | Corruption of Site Prevents Access to Valid Material | R | Technology - Operational Environment
3 | Amount of Storage Used Exceeds Capacity available under Hosting Agreement | R | Technology - Support
4 | Hosting Service Announces Hosting Plan No Longer Available | R | Environmental - Business/Economic
5 | Domain-Name Lease Lapses and Is Appropriated by Another | R | People - Management
6 | Incapacity of Developer Makes It Necessary to Transfer Domain | R | People - Personnel
7 | No Sponsors Available When Necessary to Pass On Support | R | People - Sponsors
8 | Computer Failure Loses Image of Current Site Content | R | Technology - Support
9 | Computer Failure Loses History of Site Content | R | Technology - Support
10 | Site Development Software Becomes Unsupported | R | Technology - Support
11 | Site Development Software Not Usable on New Computer | R | Technology - Support
12 | Operating System for Site Development Becomes Unsupported | R | Technology - Support
13 | Internet Connectivity Interrupted by External Events | R | Environmental - Technology
14 | Development Computers Lost in Disaster | R | Environmental - Technology
15 | Local Copies of Assets Lost in Disaster | R | Environmental - Technology
16 | Incapacity of Developer Makes It Necessary to Transfer Assets | R | People - Personnel
17 | Denial-of-Service Attack makes Web Site Inaccessible | R | Technology - Security
18 | Operator Error Corrupts Site and Mirror Images | R | People - Skills
19 | Backup of Site Assets is Not Usable to Recover System and Site | R | Technology - Operational Environment
20 | ODMA Software becomes unusable on new Windows Releases | R | Technology - Availability
21 | New Applications Releases withdraw ODMA Support | R | Technology - Availability
22 | Developer Interest Disappears because of reduced use of ODMA | R | People - Personnel
23 | Windows Installation Requirements become too costly to support | R | Environmental - Economic
24 | Configuration and Troubleshooting too difficult for users | R | People - End-Users
25 | Forking of ODMA Fragments Support/User Community | R | Technology - Deployment
26 | Discussion Lists at AIIM Not Maintained | R | People - Stakeholders
27 | Support for ODMA-aware applications is abandoned | R | Environmental - Competition
28 | Existing ODMA-aware applications become obsolete | R | Technology - Support
29 | Proprietary Software cannot be tested by troubleshooter | R | Environmental - Economic
30 | Compilers for Building ODMA software are obsolete and new ones must be obtained. | R | Technology - Development & Test
31 | Users cannot find ODMA Support for Questions & Requests | R | Technology - Support
32 | Adopters abandon ODMA because too difficult to develop | R | People - Skills
33 | ODMA Incompatible with Newer Operating Systems | R | Technology - Availability
34 | Site Fails to Meet Standards for Accessibility | R | Environment - Legal
Note on C5: orcmid: X designates a concern, issue, or problem. R designates a risk
Note on D5: orcmid: There are actions only for non-risk items. Typical actions are "consolidate," "escalate," "refer," "restate," and "treat as out of scope." I use the risk classification when a Risk is identified

## Risk Analysis & Prioritization
Risk ID# | Identified Risk | Priority / Order | Probability (17, 50, 84%) | Impact (1, 10, 100) | Exposure (0 to 100) | Exposure Recipient
7 | No Sponsors Available When Necessary to Pass On Support | 1 | 0.5 | 100 | 50 | All
9 | Computer Failure Loses History of Site Content | 2 | 0.5 | 100 | 50 | NuovoDoc
24 | Configuration and Troubleshooting too difficult for users | 3 | 0.5 | 100 | 50 | All
26 | Discussion Lists at AIIM Not Maintained | 4 | 0.5 | 100 | 50 | All
31 | Users cannot find ODMA Support for Questions & Requests | 5 | 0.5 | 100 | 50 | All
5 | Domain-Name Lease Lapses and Is Appropriated by Another | 6 | 0.17 | 100 | 17 | NuovoDoc
6 | Incapacity of Developer Makes It Necessary to Transfer Domain | 7 | 0.17 | 100 | 17 | Hamilton
10 | Site Development Software Becomes Unsupported | 8 | 0.17 | 100 | 17 | All
11 | Site Development Software Not Usable on New Computer | 9 | 0.17 | 100 | 17 | All
14 | Development Computers Lost in Disaster | 10 | 0.17 | 100 | 17 | NuovoDoc
15 | Local Copies of Assets Lost in Disaster | 11 | 0.17 | 100 | 17 | NuovoDoc
16 | Incapacity of Developer Makes It Necessary to Transfer Assets | 12 | 0.17 | 100 | 17 | NuovoDoc
19 | Backup of Site Assets is Not Usable to Recover System and Site | 13 | 0.17 | 100 | 17 | All
25 | Forking of ODMA Fragments Support/User Community | 14 | 0.17 | 100 | 17 | All
1 | Loss of Connectivity to Site Prevents Updating | 15 | 0.5 | 10 | 5 | NuovoDoc
22 | Developer Interest Disappears because of reduced use of ODMA | 16 | 0.5 | 10 | 5 | All
23 | Windows Installation Requirements become too costly to support | 17 | 0.5 | 10 | 5 | Developers
29 | Proprietary Software cannot be tested by troubleshooter | 18 | 0.5 | 10 | 5 | All
30 | Compilers for Building ODMA software are obsolete and new ones must be obtained. | 19 | 0.5 | 10 | 5 | Developers
32 | Adopters abandon ODMA because too difficult to develop | 20 | 0.5 | 10 | 5 | All
33 | ODMA Incompatible with Newer Operating Systems | 21 | 0.5 | 10 | 5 | All
34 | Site Fails to Meet Standards for Accessibility | 22 | 0.5 | 10 | 5 | All
3 | Amount of Storage Used Exceeds Capacity available under Hosting Agreement | 23 | 0.17 | 10 | 1.7 | NuovoDoc
4 | Hosting Service Announces Hosting Plan No Longer Available | 24 | 0.17 | 10 | 1.7 | NuovoDoc
12 | Operating System for Site Development Becomes Unsupported | 25 | 0.17 | 10 | 1.7 | All
13 | Internet Connectivity Interrupted by External Events | 26 | 0.17 | 10 | 1.7 | All
17 | Denial-of-Service Attack makes Web Site Inaccessible | 27 | 0.17 | 10 | 1.7 | All
18 | Operator Error Corrupts Site and Mirror Images | 28 | 0.17 | 10 | 1.7 | NuovoDoc
20 | ODMA Software becomes unusable on new Windows Releases | 29 | 0.17 | 10 | 1.7 | All
21 | New Applications Releases withdraw ODMA Support | 30 | 0.17 | 10 | 1.7 | All
27 | Support for ODMA-aware applications is abandoned | 31 | 0.17 | 10 | 1.7 | All
28 | Existing ODMA-aware applications become obsolete | 32 | 0.17 | 10 | 1.7 | All
8 | Computer Failure Loses Image of Current Site Content | 33 | 0.5 | 1 | 0.5 | NuovoDoc
2 | Corruption of Site Prevents Access to Valid Material | 34 | 0.17 | 1 | 0.17 | Users

## Disclaimer
Ó 2002 Microsoft Corporation. All rights reserved.
The information contained in this document represents the current view of Microsoft Corporation on the issues discussed as of the date of publication. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information presented after the date of publication.
This document is for informational purposes only. MICROSOFT MAKES NO WARRANTIES, EXPRESS OR IMPLIED, IN THIS DOCUMENT.